## Generic research project Gantt
| 2023 | [6 empty] | 2024 | [12 empty] | 2025
| Jul |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb |  | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
A: Governance & Management | A: Governance & Management
A1: Project Governance Committee
A2: Core Team Meetings
A3: Reports to Funders
B: Research Plan/Protocol | B: Research Plan
B1: Research Question(s)
B2: Method
B3: Approved Full Plan
C: Data |  |  | C: Data
C1: Potential Data Sources
C2: Selected Data Sources
C3: Raw Data/Inputs | [5 empty] | data approvals |  |  |  | data collection
D: Analyses & Results | [11 empty] | D: Analyses & Results
E: Knowledge to Action (KT/KM) |  | E: Knowledge to Action (KT/KM)
E1: Mtgs w Knowledge Users
E2: Publications
E3: Other KT/KM Deliverables (TBD)
| Jul |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb |  | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
| 2023 | [6 empty] | 2024 | [12 empty] | 2025
CC BY-NC 2.0 Research Project Management (RPM). No attribution required when tool is modified and used as part of the planning or implementation of research.
See www.researchpm.com for webinars, workshops, and other resources to support use.
all approvals to commence research secured
data collection complete
public report

## Pragmatic trial Gantt
Deliverable/ Subdeliverable Name | Q2 2022 |  | Q3 2022 |  | Q4 2022 | Q1 2023 | Q2 2023 | Q3 2023 | Q4 2023 | Q1 2024 | Q2 2024 | Q3 2024 |  | Q4 2024
A: Governance & Management | A: Governance & Management
A1: Steering Committee Meetings
A2: Core Team Meetings
A3: Reports
B: Research Protocol |  | B: Research Protocol
B1: Research Questions
B2: Research Ethics Approval
B3: Data Access Approval
C: Data Acquisition |  |  | C: Data Acquisition
C1: Data Management System
C2: Site/Participant Recruitment
C3: Data
D: Analyses & Results | [9 empty] | D: Analyses & Results
E: Knowledge Translation (KT) |  | E: Knowledge Translation (KT)
E1: Mtgs w Knowledge Users
E2: Peer-reviewed Publications |  |  |  | protocol | [8 empty] | study results
E3: Other KT TBD
CC BY-NC 2.0 Research Project Management (RPM). No attribution required when tool is modified and used as part of the planning or implementation of research.
See www.researchpm.com for webinars, workshops, and other resources to support use.
priorities and research questions articulated and shared with team, knowledge users (KUs) and other stakeholders
last approval secured
data collection complete

## PDSA Gantt
| Q4 2022/23 | [5 empty] | Q1 2023/24 | [5 empty] | Q2 2023/24 | [5 empty] | Q3 2023/24 |  |  |  | Q4 2023/24
Deliverable | Oct |  | Nov |  | Dec |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug | Sep | Oct | Nov | Dec
A: Planning & Management | A: Planning & Management
A1: Core Team Meetings
A2: Literature Review
A3: Driver Diagram
A3: Bimonthly Progress Reports
B: Plan Do Study Act (PDSA) Iterations |  | B: Plan Do Study Act (PDSA) Iterations
B1: Plan for 1st Change
B2: PDSA Iterations |  |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9
B3: Analyzed Outcomes |  |  |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9
B4: Documented Final Process
C: Implemented Improved Process | [20 empty] | C: Process
C1: Process Document for Stakeholders
C2: Lessons Learned
C3: Plan for Implementation
CC BY-NC 2.0 Research Project Management (RPM). No attribution required when tool is modified and used as part of the planning or implementation of research.
See www.researchpm.com for webinars, workshops, and other resources to support use.

## template calendar year
| 2023 | [11 empty] | 2024 | [11 empty] | 2025
Deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| 2023 | [11 empty] | 2024 | [11 empty] | 2025
See www.researchpm.com for webinars, workshops, and other resources to support use.

## template quarters
| Year 1 |  |  |  | Year 2 |  |  |  | Year 3
Deliverables | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
See www.researchpm.com for webinars, workshops, and other resources to support use.

## template fiscal year
| Q4 2022/23 |  |  | Q1 2023/24 |  |  | Q2 2023/24 |  |  | Q3 2023/24 |  |  | Q4 2023/24 |  |  | Q1 2024/25 |  |  | Q2 2024/25 |  |  | Q3 2024/25 |  |  | Q4 2024/25 |  |  | Q1 2025/26
Deliverable | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
See www.researchpm.com for webinars, workshops, and other resources to support use.