## project tracking template
Deliverable/ Subdeliverable Name | Lead Initials | Last Accomplishment or Completed Task/Milestone | Status (Green, Yellow, Red) | Upcoming Tasks/Milestones and Target Completion Dates (changes relative to last version highlighted with blue, italic, bold font)
|  |  |  | Task/Milestone 1 | Task/Milestone 2 | Task/Milestone 3 | Task/Milestone 4 | Task/Milestone 5 | Task/Milestone 6
Green: progressing well and within schedule/budget constraints, issues and negative risks (if any) are minor and likely to be resolved without affecting other deliverables
Yellow: low impact negative risks have been realized and/or medium or high impact negative risks have potential to be realized in the near future that could necessitate changes for deliverable and/or planning
Red: progress halted, significant decisions and/or activities required to bring deliverable back on track

## Generic Research 15Sep2023
Deliverable/ Subdeliverable Name | Lead Initials | Last Accomplishment or Completed Task/Milestone | Status (Green, Yellow, Red) | Upcoming Tasks/Milestones and Target Completion Dates (changes relative to last version highlighted with blue, italic, bold font)
|  |  |  | Task/Milestone 1 | Task/Milestone 2 | Task/Milestone 3 | Task/Milestone 4 | Task/Milestone 5 | Task/Milestone 6
A1: Project Governance Committee | EP | Members of Governance Committee confirmed 11Sep2023, first meeting scheduled to be on 10Oct2023) | Green | Set agenda for 1st committee meeting (late Sep2023) | First committee meeting (10Oct2023) | Circulate record of decisions and action items (~late Oct2023)
A2: Core Team Meetings | SCM | Monthly Core Team meetings occuring, in-person meeting scheduled to be from Oct 9-11, 2023 (~ 1 month earlier than planned) | Yellow | Book meeting room and accommodations for in-person meeting (late-Sep2023) | Establish in-person meeting agenda including speakers, breakout groups, and social activities (3Oct2023) | Hold in-person meeting (Oct 9-11,2023)
A3: Reports to Funders | EP | None to-date | Green | Begin gathering information for first Report (mid-Jan2024) | Share draft Report with SCM and core team (mid-Feb2024) | Share near final Report with Governance Committee (early Mar2024) | Submit final Report incorporating edits (if any) from Governance Committee (no later than 31 Mar2024) | Begin gathering information for first Report (mid-Jul2024) | Share draft Report with SCM and core team (mid-Aug2024)
B1: Priorities/ Question(s) | SCM | Research questions reviewed and refined by Core Team (10Aug2023) | Green | Confirm final research question with Governance Committee at first committee meeting (target early Oct2023)
B2: Method | SCM | None to-date | Yellow | Assess suitability of methods from grant application in light of revised research question(s) (late Sep2023) | Share planned methods/methodology as an FYI at first Governance Committee meeting (10Oct2023)
B3: Approved Full Plan | EP | None to-date | not started | Initiate work on full protocol to be submitted for Research Ethics Board approval (early Nov2023) | Finalize protocol based on Governance Committee feedback on research questions (late Nov2023) | REB approval received (target mid-Dec2023)
C1: Potential Data Sources | JD | Core team identified two potential new data sources to explore at July meeting (13Jul2023) | Green | Ask stakeholders about additional potential data sources (complete by late-Oct2023) | Finalize list of potential data sources (late Oct2023)
C2: Selected Data Sources | JD | None to-date | not started | Discuss and agree on data sources at Oct core team meeting (mid-Oct2023) | Finalize complied data sources list (late Oct2023)
C3: Raw Data/Inputs | JD | None to-date | not started | Initiate preparation of data access application (early Nov2023) | Complete data access application (late Nov2023) | All approvals related to data received (mid-Feb2024) | Data collection starts (late Feb2024) | Data collection ends (late Oct2024)
D: Analyses & Results | EP | None to-date | not started | Target date to start analyses is early Apr2024 | Target date to complete analyses is mid-Feb2025
E1: Mtgs w Knowledge Users | JD | Meetings with policy makers (2) and intended beneficiaries (6) completed 8Sep2023 | Green | Review and refine proposed priorities and research questions with policy makers and intended beneficiaries Oct2023 | Send email updates every ~2-3 months | Meet with stakeholders to discuss preliminary and early findings (mid-Sep2024 to mid-Oct2024) | Meet with stakeholders to discuss final results and to involve them in knowledge translation and dissemination (mid-Feb2025 to late Mar2025)
E2: Publications | SCM | None to-date | not started
E3: Other KT/KM Deliverables (TBD) | TBD | Details to be added as deliverables are defined. | not started
Green: progressing well and within schedule/budget constraints, issues and negative risks (if any) are minor and likely to be resolved without affecting other deliverables
Yellow: low impact negative risks have been realized and/or medium or high impact negative risks have potential to be realized in the near future that could necessitate changes for deliverable and/or planning
Red: progress halted, significant decisions and/or activities required to bring workstream back on track
CC BY-NC 4.0 Research Project Management (RPM), see www.researchpm.com for webinars, workshops, and other guidance to support use

## Generic Research 20Jul2023
Deliverable/ Subdeliverable Name | Lead Initials | Last Accomplishment or Completed Task/Milestone | Status (Green, Yellow, Red) | Upcoming Tasks/Milestones and Target Completion Dates (changes relative to last version highlighted with blue, italic, bold font)
|  |  |  | Task/Milestone 1 | Task/Milestone 2 | Task/Milestone 3 | Task/Milestone 4 | Task/Milestone 5 | Task/Milestone 6
A1: Project Governance Committee | EP | None to-date | Green | Short list of potential committee members (mid-Aug2023) | Invitations sent to potential members (late Aug-2023) | Confirmed membership (mid-Sep2023) | Set date and agenda for 1st committee meeting (late Sep2023) | First committee meeting (early Oct2023) | Circulate record of decisions and action items (~late Oct2023)
A2: Core Team Meetings | SCM | Monthly Core Team meetings initiated (usually the second Thursday of each month 10am Eastern) | Green | Establish in-person meeting planning committee (subset of core team) (early Aug2023) | Use doodle poll to set date for in-person meeting (mid-Aug2023) | Book meeting room and accommodations for in-person meeting (mid-Sep2023) | Establish in-person meeting agenda including speakers, breakout groups, and social activities (mid-Oct2023) | Hold in-person meeting (exact date TBC, aim for before mid-Nov2023)
A3: Reports to Funders | EP | None to-date | Green | Begin gathering information for first Report (mid-Jan2024) | Share draft Report with SCM and core team (mid-Feb2024) | Share near final Report with Governance Committee (early Mar2024) | Submit final Report incorporating edits (if any) from Governance Committee (no later than 31 Mar2024) | Begin gathering information for first Report (mid-Jul2024) | Share draft Report with SCM and core team (mid-Aug2024)
B1: Priorities/ Question(s) | SCM | Research questions from grant application updated based on a review of the literature (15Jul2023) | Green | Review and refine research questions at August core team meeting | Confirm final research question with Governance Committee at first committee meeting (target early Oct2023)
B2: Method | SCM | None to-date | not started | Assess suitability of methods from grant application in light of revised research question(s) (mid-Sep2023) | Share planned methods/methodology as an FYI at first Governance Committee meeting (target early Oct2023)
B3: Approved Full Plan | EP | None to-date | not started | Initiate work on full protocol to be submitted for Research Ethics Board approval. | Finalize protocol based on Governance Committee feedback on research questions (late Oct2023)
C1: Potential Data Sources | JD | Core team identified two potential new data sources to explore at July meeting (13Jul2023) | Green | Ask stakeholders about additional potential data sources (complete by late-Oct2023) | Finalize list of potential data sources (late Oct2023)
C2: Selected Data Sources | JD | None to-date | not started | Discuss and agree on data sources at Oct core team meeting (mid-Oct2023) | Finalize complied data sources list (late Oct2023)
C3: Raw Data/Inputs | JD | None to-date | not started | Initiate preparation of data access application (early Nov2023) | Complete data access application (late Nov2023) | All approvals related to data received (mid-Feb2024) | Data collection starts (late Feb2024) | Data collection ends (late Oct2024)
D: Analyses & Results | EP | None to-date | not started | Target date to start analyses is early Apr2024 | Target date to complete analyses is mid-Feb2025
E1: Mtgs w Knowledge Users | JD | Meeting with policy makers scheduled for 27Jul2023 | Green | Schedule small group meetings with people from intended beneficiary groups Aug2023 | Review and refine proposed priorities and research questions with policy makers and intended beneficiaries Oct2023 | Send email updates every ~2-3 months | Meet with stakeholders to discuss preliminary and early findings (mid-Sep2024 to mid-Oct2024) | Meet with stakeholders to discuss final results and to involve them in knowledge translation and dissemination (mid-Feb2025 to late Mar2025)
E2: Publications | SCM | None to-date | not started
E3: Other KT/KM Deliverables (TBD) | TBD | Details to be added as deliverables are defined. | not started
Green: progressing well and within schedule/budget constraints, issues and negative risks (if any) are minor and likely to be resolved without affecting other deliverables
Yellow: low impact negative risks have been realized and/or medium or high impact negative risks have potential to be realized in the near future that could necessitate changes for deliverable and/or planning
Red: progress halted, significant decisions and/or activities required to bring workstream back on track
CC BY-NC 4.0 Research Project Management (RPM), see www.researchpm.com for webinars, workshops, and other guidance to support use

## program or centre template
Workstream or Project | Lead Initials | Last Accomplishment or Completed Milestone | Status (Green, Yellow, Red) | Upcoming Milestones and Target Completion Dates (changes relative to last version highlighted with blue, italic, bold font)
|  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6
Governance Body(ies)
Team Meetings
Reports
Portfolio Risk Management Plan
Project 1
Project 2
Project 3
Project 4
Project 5
Project 6
Project 7
Project 8
Project 9
Project 10
Green: progressing well and within schedule/budget constraints, issues (if any) are minor and likely to be resolved without affecting other projects or operations
Yellow: low impact risks have been realized and/or medium or high impact risks have potential to be realized in the near future that could necessitate changes
Red: progress halted, significant decisions and/or activities required to bring back on track

## fictional centre 18Dec2023
Workstream or Project | Lead Initials | Last Accomplishment or Completed Milestone | Status (Green, Yellow, Red) | Upcoming Milestones and Target Completion Dates (changes relative to last version highlighted with blue, italic, bold font)
|  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6
A1: Steering Committee | MJF | Second Steering Committee meeting on 7Dec2023 including CCA presentation | Green | Finalize notes and action items for meeting and post online 21Dec2023 | Confirm researcher presenter for next Board meeting by 6Feb2024 | Circulate meeting pack for 6Mar2024 meeting by 28Feb2024 | Confirm researcher presenter for next Board meeting by 7Nov2023 | Circulate meeting pack for 7Dec2023 meeting by 30Nov2023 | Hold 7Dec2023 meeting
A2: Team Meetings | BT | Meetings of co-investigators occuring as scheduled, will move to 2nd Tuesday of each month beginning Feb with additional meetings scheduled as needed | Green | Meeting 9Jan2024 | Meeting 23Jan2024 | Meetings on 2nd Tuesday of each month beginning 13Feb2024 (future meeting dates will no longer be captured in tracking sheet)
A3: Operational Plan | MFJ | Steering Committee approved year 1 operational plan | Green | First draft of years 2-3 operational plan Jun2024 | Refined draft years 2-3 operational plan Sep2024 | Years 2-3 operational plan presented to Steering Committee Sep2024 mtg (date TBD)
A4: Reports to Stakeholders & Funders | SF | Progress report submitted to funder one week ahead of schedule on 4Oct2023 | Green | Begin compiling information for second progress report 15Jul2024 | Presented draft progress report to Steering Committee at Sep2024 meeting (date TBD) | Share revised report with Chair of Steering Committee late-Sep2024 | Submit progress report to funder mid-Oct2024 | Begin compiling information for second progress report mid-Jul2025
A5: Sustainability Plan | MJF |  | not started | Work on Sustainability Plan to begin no later than Jan2025
B1: Physical Space | AGD | Potential sites further from university and alternative smaller space floor plan developed - Nov2023 | Yellow | Short list of suitable spaces mid-Dec2023 | Compile information about options for 9Jan2024 team meeting | Short-list of physcial spaces - mid-Jan2024 | Selected site Feb2024
B2: Furnishings & Equipment |  |  | not started
B3: Staff | AGD | COO AGD started 7Oct2023 | Green | Posting for Communications Officer and Research Coordinator 10Jan2024 | Offers for Communications Officer and Research Coordinator 31Mar2024 | HR plan for years 2-3 (as part of Operational Plan) Aug2024
B4: Website |  |  | not started | Aim to start website development no later than fall 2024 and have initial website launched in early 2025
B5: Social Media & Newsletters |  |  | not started
C1: Program 1 | CCA | Two of three pathfinder project kick-off meetings held - Nov/Dec2023 | Green | Third pathfinder project teams kickoff meetings 10Jan2024 | Target 2 grant applications by Sep2024 | Mid-term updates from pathfinder projects - Sep2024 | Results from pathfinder projects - Jul2025
C2: Program 2 | FJA | Meeting of co-investigators and agreement on 3 pathfinder projects and 2 grant applications to prepare | Green | Three pathfinder project teams have kickoff meetings by mid-Feb2024 | Target 2 grant applications by Oct2024 | Mid-term updates from pathfinder projects - Dec2024 | Results from pathfinder projects - Sep2025
C3: Program 3 |  |  | not started
D1: Seminar Series |  |  | not started
D2: Stakeholder Meetings | MJF | First researcher stakeholder meeting mid-Nov2023, two stakeholders confirmed as members of Steering Committee | Green | Stakeholder engagement plan by March 2024
D3: Annual Summit |  |  | not started
E1: Fellowships |  |  | not started
E2: Workshops |  |  | not started
E3: Seed Funding |  |  | not started
Green: progressing well and within schedule/budget constraints, issues (if any) are minor and likely to be resolved without affecting other projects or operations
Yellow: low impact risks have been realized and/or medium or high impact risks have potential to be realized in the near future that could necessitate changes
Red: progress halted, significant decisions and/or activities required to bring back on track
Workstreams for Phase 1
A: Governance & Management
B: Facilities, Staffing & Communications
C: Research
D: Knowledge Translation
E: Training & Capacity Building
CC BY-NC 4.0 Research Project Management (RPM), see www.researchpm.com for webinars, workshops, and other guidance to support use

## fictional centre 13Sep2023
Workstream or Project | Lead Initials | Last Accomplishment or Completed Milestone | Status (Green, Yellow, Red) | Upcoming Milestones and Target Completion Dates (changes relative to last version highlighted with blue, italic, bold font)
|  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6
A1: Steering Committee | MJF | First Steering Committee meeting on 8Sep2023 | Green | Confirm researcher presenter for next Board meeting by 7Nov2023 | Circulate meeting pack for 7Dec2023 meeting by 30Nov2023 | Hold 7Dec2023 meeting | Finalize notes and action items for meeting and post online 21Dec2023 | Confirm researcher presenter for next Board meeting by 6Feb2024 | Circulate meeting pack for 6Mar2024 meeting by 28Feb2024
A2: Team Meetings | BT | Meeting on 24Aug2023, summary notes and action items here | Green | 15Sep2023 meeting | 27Sep2023 meeting | 4Oct2023 meeting | 11Oct2023 meeting | 18Oct2023 meeting | 25Oct2023 meeting
A3: Operational Plan | MFJ | Steering Committee approved year 1 operational plan | Green | First draft of years 2-3 operational plan Jun2024 | Refined draft years 2-3 operational plan Sep2024 | Years 2-3 operational plan presented to Steering Committee Sep2024 mtg (date TBD)
A4: Reports to Stakeholders & Funders | SF | Presented draft progress report to Steering Committee 8Sep2023 | Green | Share revised report with Chair of Steering Committee 22Sep2023 | Submit progress report to funder 11Oct2023 | Begin compiling information for second progress report 15Jul2024 | Presented draft progress report to Steering Committee at Sep2024 meeting (date TBD) | Share revised report with Chair of Steering Committee late-Sep2024 | Submit progress report to funder mid-Oct2024
A5: Sustainability Plan | MJF |  | not started | Work on Sustainability Plan to begin no later than Jan2025
B1: Physical Space | MJF | Initial review of available space near university did not identify any options within anticipated budget | Yellow | Develop long list of spaces with 3 km of university mid-Nov2023 | Develop alternative hybrid and hotelling office plan by mid-Nov2023 | Short list of suitable spaces mid-Dec2023 | Compile information about options for 9Jan2024 team meeting | Short-list of physcial spaces - mid-Jan2024 | Selected site Feb2024
B2: Furnishings & Equipment |  |  | not started
B3: Staff | MJF | COO competition completed 2023Jul2023 | Green | COO to start 7Oct2023 | Posting for Communications Officer and Research Coordinator 10Jan2024 | Offers for Communications Officer and Research Coordinator 31Mar2024 | HR plan for years 2-3 (as part of Operational Plan) Aug2024
B4: Website |  |  | not started | Aim to start website development no later than fall 2024 and have initial website launched in early 2025
B5: Social Media & Newsletters |  |  | not started
C1: Program 1 | JCV | Meeting of co-investigators and agreement on 3 pathfinder projects and 2 grant applications to prepare | Green | Three pathfinder project teams have kickoff meetings by mid-Dec2023 | Target 2 grant applications by Sep2024 | Mid-term updates from pathfinder projects - Sep2024 | Results from pathfinder projects - Jul2025
C2: Program 2 |  |  | not started
C3: Program 3 |  |  | not started
D1: Seminar Series |  |  | not started
D2: Stakeholder Meetings | MJF |  | Green | First researcher stakeholder meeting mid-Nov2023 | Addition of two stakeholders to Steering Committee 21Dec2023 | Stakeholder engagement plan by March 2024
D3: Annual Summit |  |  | not started
E1: Fellowships |  |  | not started
E2: Workshops |  |  | not started
E3: Seed Funding |  |  | not started
Green: progressing well and within schedule/budget constraints, issues (if any) are minor and likely to be resolved without affecting other projects or operations
Yellow: low impact risks have been realized and/or medium or high impact risks have potential to be realized in the near future that could necessitate changes
Red: progress halted, significant decisions and/or activities required to bring back on track
Workstreams for Phase 1
A: Governance & Management
B: Facilities, Staffing & Communications
C: Research
D: Knowledge Translation
E: Training & Capacity Building
CC BY-NC 4.0 Research Project Management (RPM), see www.researchpm.com for webinars, workshops, and other guidance to support use