## Generic research project Gantt
| 2024 | [6 empty] | 2025 | [11 empty] | 2026
| Jul |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
A: Governance & Management | A: Governance & Management
A1: Project Governance Committee
A2: Core Team Meetings
A3: Reports to Funders
B: Research Plan/Protocol | B: Research Plan/Protocol
B1: Research Question(s)
B2: Method
B3: Approved Plan/Protocol
C: Data |  |  |  | C: Data
C1: Prep/Approvals for Data
C2: Raw Data Collection
C3: Analyses-Ready Data
D: Analyses & Results | [10 empty] | D: Analyses & Results
E: Knowledge to Action (KT/KM) |  | E: Knowledge to Action (KT/KM)
E1: Mtgs w Knowledge Users
E2: Publications
E3: Other KT/KM Deliverables (TBD)
| Jul |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
| 2024 | [6 empty] | 2025 | [11 empty] | 2026
CC BY-NC 2.0 Research Project Management (RPM). No attribution is required, and this footer can be deleted, when used for project management purposes. Use for commercial purposes is prohibited.
See www.researchpm.com for resources and training to support use.
all approvals to commence research secured
all data available for analyses
public report

## Pragmatic trial Gantt
Deliverable/ Subdeliverable Name | Q2 2022 |  | Q3 2022 |  | Q4 2022 | Q1 2023 | Q2 2023 | Q3 2023 | Q4 2023 | Q1 2024 | Q2 2024 | Q3 2024 |  | Q4 2024
A: Governance & Management | A: Governance & Management
A1: Steering Committee Meetings
A2: Core Team Meetings
A3: Reports
B: Research Protocol |  | B: Research Protocol
B1: Research Questions
B2: Research Ethics Approval
B3: Data Access Approval
C: Data Acquisition |  |  | C: Data Acquisition
C1: Data Management System
C2: Site/Participant Recruitment
C3: Data
D: Analyses & Results | [9 empty] | D: Analyses & Results
E: Knowledge Translation (KT) |  | E: Knowledge Translation (KT)
E1: Mtgs w Knowledge Users
E2: Peer-reviewed Publications |  |  |  | protocol | [8 empty] | study results
E3: Other KT TBD
CC BY-NC 2.0 Research Project Management (RPM). No attribution is required, and this footer can be deleted, when used for project management purposes. Use for commercial purposes is prohibited.
See www.researchpm.com for resources and training to support use.
priorities and research questions articulated and shared with team, knowledge users (KUs) and other stakeholders
last approval secured
data collection complete

## PDSA Gantt
| Q3 2024/25 | [5 empty] | Q4 2024/25 | [5 empty] | Q1 2025/26 | [5 empty] | Q2 2025/26 |  |  |  | Q3 2025/26
Deliverable | Oct |  | Nov |  | Dec |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug | Sep | Oct | Nov | Dec
A: Planning & Management | A: Planning & Management
A1: Core Team Meetings
A2: Literature Review
A3: Driver Diagram
A3: Bimonthly Progress Reports
B: Plan Do Study Act (PDSA) Iterations |  | B: Plan Do Study Act (PDSA) Iterations
B1: Protocol for 1st Iteration
B2: PDSA Iterations |  |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9
B3: Analyzed Outcomes |  |  |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9
B4: Documented Final Process
C: Implemented Improved Process | [20 empty] | C: Process
C1: Process Document for Stakeholders
C2: Lessons Learned
C3: Plan for Implementation
CC BY-NC 2.0 Research Project Management (RPM). No attribution is required, and this footer can be deleted, when used for project management purposes. Use for commercial purposes is prohibited.
See www.researchpm.com for resources and training to support use.

## template calendar year
| 2024 | [11 empty] | 2025 | [11 empty] | 2026
Deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| 2024 | [11 empty] | 2025 | [11 empty] | 2026
See www.researchpm.com for resources and training to support use.

## template quarters
| Year 1 |  |  |  | Year 2 |  |  |  | Year 3
Deliverables | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
See www.researchpm.com for resources and training to support use.

## template fiscal year
| Q4 2024/25 |  |  | Q1 2025/26 |  |  | Q2 2025/26 |  |  | Q3 2025/26 |  |  | Q4 2025/26 |  |  | Q1 2026/27 |  |  | Q2 2026/27 |  |  | Q3 2026/27 |  |  | Q4 2026/27 |  |  | Q1 2027/28
Deliverable | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
See www.researchpm.com for resources and training to support use.