## Slide 1
Research Project
A: Governance & Management
A1: Project Governance Committee
A2: Core Team Meetings
A3: Reports to Funders
B: Research Plan/Protocol
B1: Research Question(s)
B2: Method
B3: Approved Plan/Protocol
C: Data
C1: Prep/Approvals for Data
D: Analyses & Results
E: Knowledge to Action (KT/KM)
E1: Mtgs w Knowledge Users
E2: Publications
E3: Other KT/KM Deliverables TBD
C2: Raw Data
C3: Analyses-Ready Data
WBS for Generic Research Project

## Slide 2
Research Project
A: Governance & Management
A1: Project Governance Committee
A2: Core Team Meetings
A3: Reports to Funders
B: Research Plan/Protocol
B1: Research Question(s)
B2: Method
B3: Approved Plan/Protocol
C: Data
C1: Prep/Approvals for Data
E: Knowledge to Action (KT/KM)
E1: Mtgs w Knowledge Users
E2: Publications
E3: Other KT/KM Deliverables TBD
F: Training & Capacity Building
F1: Mentoring Program
F2: Journal Club
F3: Community of Practice
C2: Raw Data
C3: Analyses-Ready Data
D: Analyses & Results
WBS for Generic Research Project with Training & Capacity Building Workstream

## Slide 3
A: Governance & Management
Generic Pragmatic Trial
A1: Steering Committee Meetings
A2: Core Team Meetings
A3: Reports
B: Research Protocol
B1: Research Questions
B2: Research Ethics Approval
B3: Data Access Approval
C: Data Acquisition
C1: Data Management System
C2: Site/Participant Recruitment
C3: Data
D: Analyses & Results
E: Knowledge Translation (KT)
E1: Mtgs w Knowledge Users
E2: Peer-reviewed Publications
E3: Other KT TBD
WBS for Generic Pragmatic Trial

## Slide 4: WBS for Generic Plan Do Study Act (PDSA) Improvement Project
Improvement Project Name
A: Management & Coordination
A1: Core Team Meetings
A4: Monthly Progress Reports
B: PDSA Iterations
B1: Protocol for 1st Iteration
B2: PDSA Iterations
B3: Analyzed Outcomes
C: Implemented Improved Process
C2: Lessons Learned
C1: Process Document for Stakeholders
C3: Plan for Implementation
C4: Implemented and Spread Process
A3: Driver Diagram
B4: Documented Final Process
A2: Literature Review

## Slide 5: WBS for Simple Program Evaluation/Assessment
Program Evaluation
C: Analyses
D: Findings
B: Data
B1: Extraction of Existing Data
A: Evaluation Plan
A2: Inventory of Available Data
A1: Evaluation Questions
A4: Description of Methods
B2: New Data Gathered for Evaluation
D1: Interim Preliminary Findings
D2: Final Report
C1: Qualitative
C2: Quantitative
A3: Outcome Measurements

## Slide 6
A: Governance & Management
A2: Core Team Meetings
A3: Clinical Site Meetings
B: Research Plan/Protocol
B1: Priorities/ Question(s)
B2: Canadian CTA dossier
B3: Health Canada & other Approvals
C: Data
C1: Data Management System
C2: Recruitment
C3: Data
D: Analyses & Results
E: Knowledge Transfer (KT)
E1: Mtgs w Knowledge Users
E2: Publication
E3: Other KT TBD
A4: Progress Reports
B2a: Administrative form
B2b: Protocol
B2c: HC protocol summary
B2d: Informed Consent Form
B2e: Investigator’s Brochure
B2f: Quality Dossier Summary
Generic Clinical Trial
A1: Steering Committee Meetings
WBS for Generic Canadian Clinical Trial

## Slide 7: WBS for Graduate Student Research Thesis Project
Graduate Student Research Thesis Project
A: Governance & Management
B: Research Question
C: Research Plan/Protocol
D: Study Prerequisites
E: Research Study
F: Knowledge Translation & Exchange (KTE)
B1: Review of Previous Dissertations
B2: Literature Review
B3: Selected Question
C1: Data Sources
D1: Ethics Approval
D3: Recruited Sites
D4: Recruited Participants
D5: All Other
E1: Data
E2: Analyses
E2a: Outcome 1
E2b: Outcome 2
C5: Req’d External Contributions
C3: Schedule
C4: Budget
A1: Monthly Meetings with Supervisor
A2: Biannual Mtgs with Advisory Committee
A5: Thesis Defence
A4: Mock Review Committee Meeting
F1: Publications
F2: Presentations
F3: Final Thesis
D2: Authority to Access Data
C2: Methods
A3:Approved Thesis Proposal

## Slide 8
A: Governance & Management (AGD)
A2: Core Team Meetings (KJH)
A3: Status Reports (KJH)
B: Research Plan (AGD)
B1: Research Question(s) (AGD)
B2: Intervention & Study Plan (AGD)
B3: Regulatory & Other Approvals (SU)
C: Study Implementation (SU)
C1: Data Management System (PAP)
C2: Recruitment (SU)
C3: Collected Data (SU)
D: Analyses & Results (SU)
E: Knowledge Translation (PAP)
E1: Mtgs w Knowledge Users (PAP)
E2: Publications (Leads TBD)
E3: Summit (PAP)
Research Study/Trial (AGD)
A1: Steering Committee Meetings (KJH)
WBS for Research Study/Trial with Deliverable/Workstream Leads’ Initials

## Slide 9: Example WBS for a Program or Portfolio with Multiple Projects
Higher Minimum Wage Evaluation
Project 1: Evaluation of Communication to Increase Awareness
Project 2: Evaluation of Recipient Experience
Project 3: Evaluation of Impact on Small Businesses
Program Governance and Management
Monthly Program Team Meetings
Program Advisory Committee Quarterly Meetings
Program Progress Reports (2 per Year)

## Slide 10
New Research Program
A: Strategic Coordination
A2: Team Google Drive
A3: Applications for Funding
A1: Team Meetings
A5: Reports to Stakeholders & Funders
B: Research Program/ Theme 1
B1: [Research Project Name]
C: Research Program/ Theme 2
B2: [Research Project Name]
B3: [Research Project Name]
C1: [Research Project Name]
C2: [Research Project Name]
D: Research Program/ Theme 3
D1: [Research Project Name]
D2: [Research Project Name]
D3: [Research Project Name]
A4: International Collaborations
WBS for New Investigator Research Portfolio

## Slide 11
New Research Centre Phase I
A: Governance & Management
A2: Core Team Meetings
A3: Operational Plan
A1: Steering Committee
A4: Reports to Stakeholders & Funders
B: Facilities, Staffing & Communications
B1: Physical Space
B2: Furnishings & Equipment
B3: Staff
B4: Website
E: Training & Capacity Building
E1: Fellowships
E3: Seed Funding
C: Research
C1: Program 1
C2: Program 2
C3: Program 3
B5: Social Media & Newsletters
A5: Sustainability Plan
D: Knowledge Translation
D1: Seminar Series
D2: Stakeholder Meetings
D3: Annual Summit
E2: Workshops
WBS for the Establishment of a New Research Center

## Slide 12: RPM PowerPoint Tips and Tricks for Work Breakdown Structures (WBSs)
Usually, it will be easiest to modify a WBS for a similar or related project, but you can also start from scratch in SmartArt
Enter all the text you want in SmartArt format no matter how messy the formatting becomes
Once you have all the text entered, use the “layout” menu under “SmartArt Design” to experiment with ways to fill the page (e.g., “both” vs. “right hanging”)
If things inadvertently get messed up, you don’t need to start again, you can just toggle between different hierarchy views to reset the WBS
Once you have your SmartArt version complete and more or less in the right configuration, make a copy of the entire slide (keeping the SmartArt version in case you need to go back and make major changes)
On the new copied version of the slide, under “SmartArt Design” select “Convert to Shapes” to obtain a ‘dumb’ version that you can edit the text box size, font size, positioning, etc.
As you prepare other documents, you can use “copy” then “paste special - text” to transfer the content from the left-hand side toolbar of the SmartArt of your WBS so you don’t have to re-enter text