## Notes
This document has English examples and templates on the first tabs, followed by French examples and templates (on the final tabs).
Les exemples et modèles en français suivent ceux en anglais (onglets vers la fin).

## project tracking template
Deliverable/ Subdeliverable Name | Lead Initials | Last Accomplishment or Completed Task/Milestone | Status (Green, Yellow, Red) | Upcoming Tasks/Milestones and Target Completion Dates (changes relative to last version highlighted with blue, italic, bold font)
|  |  |  | Task/Milestone 1 | Task/Milestone 2 | Task/Milestone 3 | Task/Milestone 4 | Task/Milestone 5 | Task/Milestone 6
Green: progressing well and within schedule/budget constraints, issues and negative risks (if any) are minor and likely to be resolved without affecting other deliverables
Yellow: low impact negative risks have been realized and/or medium or high impact negative risks have potential to be realized in the near future that could necessitate changes for deliverable and/or planning
Red: progress halted, significant decisions and/or activities required to bring deliverable back on track
See www.researchpm.com for resources and training to support use.

## Generic Research 15Sep2024
Deliverable/ Subdeliverable Name | Lead Initials | Last Accomplishment or Completed Task/Milestone | Status (Green, Yellow, Red) | Upcoming Tasks/Milestones and Target Completion Dates (changes relative to last version highlighted with blue, italic, bold font)
|  |  |  | Task/Milestone 1 | Task/Milestone 2 | Task/Milestone 3 | Task/Milestone 4 | Task/Milestone 5 | Task/Milestone 6
A1: Project Governance Committee | EP | Members of Governance Committee confirmed 11Sep2024, first meeting scheduled to be on 10Oct2024) | Green | Set agenda for 1st committee meeting (late Sep2024) | First committee meeting (10Oct2024) | Circulate record of decisions and action items (~late Oct2024)
A2: Core Team Meetings | SCM | Monthly Core Team meetings occuring, in-person meeting scheduled to be from Oct 9-11, 2024 (~ 1 month earlier than planned) | Yellow | Book meeting room and accommodations for in-person meeting (late-Sep2024) | Establish in-person meeting agenda including speakers, breakout groups, and social activities (3Oct2024) | Hold in-person meeting (Oct 9-11,2024)
A3: Reports to Funders | EP | None to-date | Green | Begin gathering information for first Report (mid-Jan2025) | Share draft Report with SCM and core team (mid-Feb2025) | Share near final Report with Governance Committee (early Mar2025) | Submit final Report incorporating edits (if any) from Governance Committee (no later than 31 Mar2025) | Begin gathering information for first Report (mid-Jul2025) | Share draft Report with SCM and core team (mid-Aug2025)
B1: Priorities/ Question(s) | SCM | Research questions reviewed and refined by Core Team (10Aug2024) | Green | Confirm final research question with Governance Committee at first committee meeting (target early Oct2024)
B2: Method | SCM | None to-date | Yellow | Assess suitability of methods from grant application in light of revised research question(s) (late Sep2024) | Share planned methods/methodology as an FYI at first Governance Committee meeting (10Oct2024)
B3: Approved Plan/Protocol | EP | None to-date | not started | Initiate work on full protocol to be submitted for Research Ethics Board approval (early Nov2024) | Finalize protocol based on Governance Committee feedback on research questions (late Nov2024) | REB approval received (target mid-Dec2024)
C1: Prep/Approvals for Data | JD | Core team identified two potential new data sources to explore at July meeting (13Jul2024) | Green | Ask stakeholders about additional potential data sources (complete by late-Oct2024) | Finalize list of potential data sources (late Oct2024) | Complete data access application (late Nov2024) | All approvals related to data received (late-Jan2025)
C2: Raw Data Collection | JD | None to-date | not started | Data collection starts (late Feb2025) | Data collection ends (mid Sep2025)
C3: Analyses-Ready Data | JD | None to-date | not started | Data cleaning/linkage etc. starts Apr2025 | All data ready for analyses by late Oct2025 |  |  | Data collection ends (late Oct2025)
D: Analyses & Results | EP | None to-date | not started | Target date to start analyses is early Apr2025 | Target date to complete analyses is mid-Feb2026
E1: Mtgs w Knowledge Users | JD | Meetings with policy makers (2) and intended beneficiaries (6) completed 8Sep2024 | Green | Review and refine proposed priorities and research questions with policy makers and intended beneficiaries Oct2024 | Send email updates every ~2-3 months | Meet with stakeholders to discuss preliminary and early findings (mid-Sep2025 to mid-Oct2025) | Meet with stakeholders to discuss final results and to involve them in knowledge translation and dissemination (mid-Feb2026 to late Mar2026)
E2: Publications | SCM | None to-date | not started
E3: Other KT/KM Deliverables (TBD) | TBD | Details to be added as deliverables are defined. | not started
Green: progressing well and within schedule/budget constraints, issues and negative risks (if any) are minor and likely to be resolved without affecting other deliverables
Yellow: low impact negative risks have been realized and/or medium or high impact negative risks have potential to be realized in the near future that could necessitate changes for deliverable and/or planning
Red: progress halted, significant decisions and/or activities required to bring workstream back on track
See www.researchpm.com for resources and training to support use.

## Generic Research 20Jul2024
Deliverable/ Subdeliverable Name | Lead Initials | Last Accomplishment or Completed Task/Milestone | Status (Green, Yellow, Red) | Upcoming Tasks/Milestones and Target Completion Dates (changes relative to last version highlighted with blue, italic, bold font)
|  |  |  | Task/Milestone 1 | Task/Milestone 2 | Task/Milestone 3 | Task/Milestone 4 | Task/Milestone 5 | Task/Milestone 6
A1: Project Governance Committee | EP | None to-date | Green | Short list of potential committee members (mid-Aug2024) | Invitations sent to potential members (late Aug-2024) | Confirmed membership (mid-Sep2024) | Set date and agenda for 1st committee meeting (late Sep2024) | First committee meeting (early Oct2024) | Circulate record of decisions and action items (~late Oct2024)
A2: Core Team Meetings | SCM | Monthly Core Team meetings initiated (usually the second Thursday of each month 10am Eastern) | Green | Establish in-person meeting planning committee (subset of core team) (early Aug2024) | Use doodle poll to set date for in-person meeting (mid-Aug2024) | Book meeting room and accommodations for in-person meeting (mid-Sep2024) | Establish in-person meeting agenda including speakers, breakout groups, and social activities (mid-Oct2024) | Hold in-person meeting (exact date TBC, aim for before mid-Nov2024)
A3: Reports to Funders | EP | None to-date | Green | Begin gathering information for first Report (mid-Jan2025) | Share draft Report with SCM and core team (mid-Feb2025) | Share near final Report with Governance Committee (early Mar2025) | Submit final Report incorporating edits (if any) from Governance Committee (no later than 31 Mar2025) | Begin gathering information for first Report (mid-Jul2025) | Share draft Report with SCM and core team (mid-Aug2025)
B1: Priorities/ Question(s) | SCM | Research questions from grant application updated based on a review of the literature (15Jul2024) | Green | Review and refine research questions at August core team meeting | Confirm final research question with Governance Committee at first committee meeting (target early Oct2024)
B2: Method | SCM | None to-date | not started | Assess suitability of methods from grant application in light of revised research question(s) (mid-Sep2024) | Share planned methods/methodology as an FYI at first Governance Committee meeting (target early Oct2024)
B3: Approved Plan/Protocol | EP | None to-date | not started | Initiate work on full protocol to be submitted for Research Ethics Board approval. | Finalize protocol based on Governance Committee feedback on research questions (late Oct2024)
C1: Prep/Approvals for Data | JD | Core team identified two potential new data sources to explore at July meeting (13Jul2024) | Green | Ask stakeholders about additional potential data sources (complete by late-Oct2024) | Finalize list of potential data sources (late Oct2024) | Complete data access application (late Nov2024) | All approvals related to data received (late-Jan2025)
C2: Raw Data Collection | JD | None to-date | not started | Data collection starts (late Feb2025) | Data collection ends (mid Sep2025)
C3: Analyses-Ready Data | JD | None to-date | not started | Data cleaning/linkage etc. starts Apr2025 | All data ready for analyses by late Oct2025
D: Analyses & Results | EP | None to-date | not started | Target date to start analyses is early Apr2025 | Target date to complete analyses is mid-Feb2026
E1: Mtgs w Knowledge Users | JD | Meeting with policy makers scheduled for 27Jul2024 | Green | Schedule small group meetings with people from intended beneficiary groups Aug2024 | Review and refine proposed priorities and research questions with policy makers and intended beneficiaries Oct2024 | Send email updates every ~2-3 months | Meet with stakeholders to discuss preliminary and early findings (mid-Sep2025 to mid-Oct2025) | Meet with stakeholders to discuss final results and to involve them in knowledge translation and dissemination (mid-Feb2026 to late Mar2026)
E2: Publications | SCM | None to-date | not started
E3: Other KT/KM Deliverables (TBD) | TBD | Details to be added as deliverables are defined. | not started
Green: progressing well and within schedule/budget constraints, issues and negative risks (if any) are minor and likely to be resolved without affecting other deliverables
Yellow: low impact negative risks have been realized and/or medium or high impact negative risks have potential to be realized in the near future that could necessitate changes for deliverable and/or planning
Red: progress halted, significant decisions and/or activities required to bring workstream back on track
See www.researchpm.com for resources and training to support use.

## program or centre template
Workstream or Project | Lead Initials | Last Accomplishment or Completed Milestone | Status (Green, Yellow, Red) | Upcoming Milestones and Target Completion Dates (changes relative to last version highlighted with blue, italic, bold font)
|  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6
Governance Body(ies)
Team Meetings
Reports
Portfolio Risk Management Plan
Project 1
Project 2
Project 3
Project 4
Project 5
Project 6
Project 7
Project 8
Project 9
Project 10
Green: progressing well and within schedule/budget constraints, issues (if any) are minor and likely to be resolved without affecting other projects or operations
Yellow: low impact risks have been realized and/or medium or high impact risks have potential to be realized in the near future that could necessitate changes
Red: progress halted, significant decisions and/or activities required to bring back on track
See www.researchpm.com for resources and training to support use.

## fictional centre 18Dec2023
Workstream or Project | Lead Initials | Last Accomplishment or Completed Milestone | Status (Green, Yellow, Red) | Upcoming Milestones and Target Completion Dates (changes relative to last version highlighted with blue, italic, bold font)
|  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6
A1: Steering Committee | MJF | Second Steering Committee meeting on 7Dec2023 including CCA presentation | Green | Finalize notes and action items for meeting and post online 21Dec2023 | Confirm researcher presenter for next Board meeting by 6Feb2024 | Circulate meeting pack for 6Mar2024 meeting by 28Feb2024 | Confirm researcher presenter for next Board meeting by 7Nov2023 | Circulate meeting pack for 7Dec2023 meeting by 30Nov2023 | Hold 7Dec2023 meeting
A2: Team Meetings | BT | Meetings of co-investigators occuring as scheduled, will move to 2nd Tuesday of each month beginning Feb with additional meetings scheduled as needed | Green | Meeting 9Jan2024 | Meeting 23Jan2024 | Meetings on 2nd Tuesday of each month beginning 13Feb2024 (future meeting dates will no longer be captured in tracking sheet)
A3: Operational Plan | MFJ | Steering Committee approved year 1 operational plan | Green | First draft of years 2-3 operational plan Jun2024 | Refined draft years 2-3 operational plan Sep2024 | Years 2-3 operational plan presented to Steering Committee Sep2024 mtg (date TBD)
A4: Reports to Stakeholders & Funders | SF | Progress report submitted to funder one week ahead of schedule on 4Oct2023 | Green | Begin compiling information for second progress report 15Jul2024 | Presented draft progress report to Steering Committee at Sep2024 meeting (date TBD) | Share revised report with Chair of Steering Committee late-Sep2024 | Submit progress report to funder mid-Oct2024 | Begin compiling information for second progress report mid-Jul2025
A5: Sustainability Plan | MJF |  | not started | Work on Sustainability Plan to begin no later than Jan2025
B1: Physical Space | AGD | Potential sites further from university and alternative smaller space floor plan developed - Nov2023 | Yellow | Short list of suitable spaces mid-Dec2023 | Compile information about options for 9Jan2024 team meeting | Short-list of physcial spaces - mid-Jan2024 | Selected site Feb2024
B2: Furnishings & Equipment |  |  | not started
B3: Staff | AGD | COO AGD started 7Oct2023 | Green | Posting for Communications Officer and Research Coordinator 10Jan2024 | Offers for Communications Officer and Research Coordinator 31Mar2024 | HR plan for years 2-3 (as part of Operational Plan) Aug2024
B4: Website |  |  | not started | Aim to start website development no later than fall 2024 and have initial website launched in early 2025
B5: Social Media & Newsletters |  |  | not started
C1: Program 1 | CCA | Two of three pathfinder project kick-off meetings held - Nov/Dec2023 | Green | Third pathfinder project teams kickoff meetings 10Jan2024 | Target 2 grant applications by Sep2024 | Mid-term updates from pathfinder projects - Sep2024 | Results from pathfinder projects - Jul2025
C2: Program 2 | FJA | Meeting of co-investigators and agreement on 3 pathfinder projects and 2 grant applications to prepare | Green | Three pathfinder project teams have kickoff meetings by mid-Feb2024 | Target 2 grant applications by Oct2024 | Mid-term updates from pathfinder projects - Dec2024 | Results from pathfinder projects - Sep2025
C3: Program 3 |  |  | not started
D1: Seminar Series |  |  | not started
D2: Stakeholder Meetings | MJF | First researcher stakeholder meeting mid-Nov2023, two stakeholders confirmed as members of Steering Committee | Green | Stakeholder engagement plan by March 2024
D3: Annual Summit |  |  | not started
E1: Fellowships |  |  | not started
E2: Workshops |  |  | not started
E3: Seed Funding |  |  | not started
Green: progressing well and within schedule/budget constraints, issues (if any) are minor and likely to be resolved without affecting other projects or operations
Yellow: low impact risks have been realized and/or medium or high impact risks have potential to be realized in the near future that could necessitate changes
Red: progress halted, significant decisions and/or activities required to bring back on track
Workstreams for Phase 1
A: Governance & Management
B: Facilities, Staffing & Communications
C: Research
D: Knowledge Translation
E: Training & Capacity Building
See www.researchpm.com for resources and training to support use.

## fictional centre 13Sep2023
Workstream or Project | Lead Initials | Last Accomplishment or Completed Milestone | Status (Green, Yellow, Red) | Upcoming Milestones and Target Completion Dates (changes relative to last version highlighted with blue, italic, bold font)
|  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6
A1: Steering Committee | MJF | First Steering Committee meeting on 8Sep2023 | Green | Confirm researcher presenter for next Board meeting by 7Nov2023 | Circulate meeting pack for 7Dec2023 meeting by 30Nov2023 | Hold 7Dec2023 meeting | Finalize notes and action items for meeting and post online 21Dec2023 | Confirm researcher presenter for next Board meeting by 6Feb2024 | Circulate meeting pack for 6Mar2024 meeting by 28Feb2024
A2: Team Meetings | BT | Meeting on 24Aug2023, summary notes and action items here | Green | 15Sep2023 meeting | 27Sep2023 meeting | 4Oct2023 meeting | 11Oct2023 meeting | 18Oct2023 meeting | 25Oct2023 meeting
A3: Operational Plan | MFJ | Steering Committee approved year 1 operational plan | Green | First draft of years 2-3 operational plan Jun2024 | Refined draft years 2-3 operational plan Sep2024 | Years 2-3 operational plan presented to Steering Committee Sep2024 mtg (date TBD)
A4: Reports to Stakeholders & Funders | SF | Presented draft progress report to Steering Committee 8Sep2023 | Green | Share revised report with Chair of Steering Committee 22Sep2023 | Submit progress report to funder 11Oct2023 | Begin compiling information for second progress report 15Jul2024 | Presented draft progress report to Steering Committee at Sep2024 meeting (date TBD) | Share revised report with Chair of Steering Committee late-Sep2024 | Submit progress report to funder mid-Oct2024
A5: Sustainability Plan | MJF |  | not started | Work on Sustainability Plan to begin no later than Jan2025
B1: Physical Space | MJF | Initial review of available space near university did not identify any options within anticipated budget | Yellow | Develop long list of spaces with 3 km of university mid-Nov2023 | Develop alternative hybrid and hotelling office plan by mid-Nov2023 | Short list of suitable spaces mid-Dec2023 | Compile information about options for 9Jan2024 team meeting | Short-list of physcial spaces - mid-Jan2024 | Selected site Feb2024
B2: Furnishings & Equipment |  |  | not started
B3: Staff | MJF | COO competition completed 2023Jul2023 | Green | COO to start 7Oct2023 | Posting for Communications Officer and Research Coordinator 10Jan2024 | Offers for Communications Officer and Research Coordinator 31Mar2024 | HR plan for years 2-3 (as part of Operational Plan) Aug2024
B4: Website |  |  | not started | Aim to start website development no later than fall 2024 and have initial website launched in early 2025
B5: Social Media & Newsletters |  |  | not started
C1: Program 1 | JCV | Meeting of co-investigators and agreement on 3 pathfinder projects and 2 grant applications to prepare | Green | Three pathfinder project teams have kickoff meetings by mid-Dec2023 | Target 2 grant applications by Sep2024 | Mid-term updates from pathfinder projects - Sep2024 | Results from pathfinder projects - Jul2025
C2: Program 2 |  |  | not started
C3: Program 3 |  |  | not started
D1: Seminar Series |  |  | not started
D2: Stakeholder Meetings | MJF |  | Green | First researcher stakeholder meeting mid-Nov2023 | Addition of two stakeholders to Steering Committee 21Dec2023 | Stakeholder engagement plan by March 2024
D3: Annual Summit |  |  | not started
E1: Fellowships |  |  | not started
E2: Workshops |  |  | not started
E3: Seed Funding |  |  | not started
Green: progressing well and within schedule/budget constraints, issues (if any) are minor and likely to be resolved without affecting other projects or operations
Yellow: low impact risks have been realized and/or medium or high impact risks have potential to be realized in the near future that could necessitate changes
Red: progress halted, significant decisions and/or activities required to bring back on track
Workstreams for Phase 1
A: Governance & Management
B: Facilities, Staffing & Communications
C: Research
D: Knowledge Translation
E: Training & Capacity Building
See www.researchpm.com for resources and training to support use.

## feuille de suivi des livrables
Nom du livrable/ sous-livrable | Initiales du responsable | Dernière tâche accomplie ou jalon terminée | État (vert, jaune, rouge) | Tâches/Jalons à venir et dates d’achèvement cibles (les changements par rapport à la dernière version sont en bleu, en italique et en gras)
|  |  |  | Tâche/Jalon 1 | Tâche/Jalon 2 | Tâche/Jalon 3 | Tâche/Jalon 4 | Tâche/Jalon 5 | Tâche/Jalon 6
Vert : Le travail avance rondement, dans le respect de l’échéancier et du budget; s’il y a des problèmes, ils sont mineurs et se régleront vraisemblablement sans aucune incidence sur les autres livrables.
Jaune : Des risques à faible impact surviennent et/ou des risques à impact moyen ou élevé pourraient survenir dans un proche avenir, ce qui pourrait obliger à modifier le livrable et/ou le projet.
Rouge : Le travail n’avance plus : sa reprise est conditionnelle à la mise en œuvre de décisions ou d’activités importantes.
Consultez le site www.researchpm.com pour obtenir des ressources et des formations afin de faciliter l'utilisation.